## general_report
SEF Jira
Displaying 43 issues at 25/Aug/15 7:01 PM.
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due Date
Story | FOUTWO-43 | Beautiful interface | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:54 | 2015-08-25 01:54
Story | FOUTWO-42 | Language Translation | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:54 | 2015-08-25 01:54
Story | FOUTWO-41 | Personal reminders | Unassigned | Zhengjie Yang | Could Have | Open | Unresolved | 2015-08-25 01:51 | 2015-08-25 01:51
Story | FOUTWO-40 | Set up second password for file or folder | Unassigned | Zhengjie Yang | Could Have | Open | Unresolved | 2015-08-25 01:50 | 2015-08-25 01:50
Story | FOUTWO-39 | Account Setting | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:50 | 2015-08-25 01:50
Story | FOUTWO-38 | Questions and Answers | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:49 | 2015-08-25 01:49
Story | FOUTWO-37 | The normalization of username and password | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:47 | 2015-08-25 01:48
Story | FOUTWO-36 | Password Cache | Unassigned | Zhengjie Yang | Could Have | Open | Unresolved | 2015-08-25 01:46 | 2015-08-25 01:46
Story | FOUTWO-35 | Enable domain name access | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:45 | 2015-08-25 01:45
Story | FOUTWO-34 | External access (WAN) | Unassigned | Zhengjie Yang | Could Have | Open | Unresolved | 2015-08-25 01:45 | 2015-08-25 01:45
Story | FOUTWO-33 | Upload user head photo | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:44 | 2015-08-25 01:44
Story | FOUTWO-32 | View media vault in grid model | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:43 | 2015-08-25 01:43
Story | FOUTWO-31 | View media vault in list model | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:42 | 2015-08-25 01:43
Story | FOUTWO-30 | Show detailed media information | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:42 | 2015-08-25 01:42
Story | FOUTWO-29 | Background music of interface | Unassigned | Zhengjie Yang | Could Have | Open | Unresolved | 2015-08-25 01:41 | 2015-08-25 01:41
Story | FOUTWO-28 | Backgroud color of interface | Unassigned | Zhengjie Yang | Could Have | Open | Unresolved | 2015-08-25 01:41 | 2015-08-25 01:41
Story | FOUTWO-27 | Recently documents | Unassigned | Zhengjie Yang | Could Have | Open | Unresolved | 2015-08-25 01:40 | 2015-08-25 01:40
Story | FOUTWO-26 | Contact us and feedback | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:40 | 2015-08-25 01:40
Story | FOUTWO-25 | Delete media files and folders | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:39 | 2015-08-25 01:39
Story | FOUTWO-24 | Drop media items and folders in recycle bin | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:38 | 2015-08-25 17:46
Story | FOUTWO-23 | Tooltip | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:38 | 2015-08-25 01:38
Story | FOUTWO-22 | Help request | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:38 | 2015-08-25 01:38
Story | FOUTWO-21 | Calculate storage capability | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:25 | 2015-08-25 01:30
Story | FOUTWO-20 | Redemption for storage expansion | Unassigned | Zhengjie Yang | Could Have | Open | Unresolved | 2015-08-25 01:24 | 2015-08-25 01:31
Story | FOUTWO-19 | Media playback in browser | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:23 | 2015-08-25 01:31
Story | FOUTWO-18 | Download media | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:18 | 2015-08-25 01:30
Story | FOUTWO-17 | Upload media - Photos, Videos, Music, Ebook | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:17 | 2015-08-25 01:31
Story | FOUTWO-16 | Save shared media files from others | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:16 | 2015-08-25 01:31
Story | FOUTWO-15 | Share media files | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:16 | 2015-08-25 01:31
Story | FOUTWO-14 | Title and description on uploads | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:15 | 2015-08-25 01:31
Story | FOUTWO-13 | Search media | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:15 | 2015-08-25 01:32
Story | FOUTWO-12 | Sort media | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:13 | 2015-08-25 01:32
Story | FOUTWO-11 | Drag and drop media to vault | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:12 | 2015-08-25 01:32
Story | FOUTWO-10 | Rename item and folder | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:12 | 2015-08-25 01:32
Story | FOUTWO-9 | Create folder | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:08 | 2015-08-25 01:32
Story | FOUTWO-8 | Modify password | Tee Ken Lau | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:08 | 2015-08-25 11:36
Story | FOUTWO-7 | Find lost user name and password | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:07 | 2015-08-25 01:32
Story | FOUTWO-6 | Log out from media vault | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:05 | 2015-08-25 01:32
Story | FOUTWO-5 | Login with verified email address | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:05 | 2015-08-25 01:32
Story | FOUTWO-4 | Create user accounts for log in | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:04 | 2015-08-25 01:32
Story | FOUTWO-3 | Mark as favourite | Unassigned | Zhengjie Yang | Should Have | Open | Unresolved | 2015-08-25 01:01 | 2015-08-25 01:33
Story | FOUTWO-2 | Browse the media vault on mobile phone | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 01:00 | 2015-08-25 01:33
Story | FOUTWO-1 | Browse the media vault on laptop | Unassigned | Zhengjie Yang | Must Have | Open | Unresolved | 2015-08-25 00:59 | 2015-08-25 01:33
Generated at Tue Aug 25 19:01:16 EST 2015 by Zhengjie Yang using JIRA 6.2.7#6265-sha1:91604a8de81892a3e362e0afee505432f29579b0.

## detailed_report
SEF Jira
Displaying 43 issues at 25/Aug/15 7:02 PM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Votes | Watchers | Description | Sprint
IFB299 042 | FOUTWO-43 | Beautiful interface | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:54 | 2015-08-25 19:00 | 2015-08-25 01:54 | 0 | 1 | User story : ● As a user, I want to be able to see a beautiful interface so that I can attracted by a beautiful interface. Acceptance Criteria : ● Flat icon design ● Some animation effect ● Good color assortment
IFB299 042 | FOUTWO-42 | Language Translation | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:54 | 2015-08-25 01:56 | 2015-08-25 01:54 | 0 | 1 | User story : ● As a user, I want to be able to translate to my own language so that I have better understanding to manage own media files effectively. Acceptance Criteria : ● Allow different language translation between English, Chinese, Japanese, Korean and French ● Responsive button is created to choose translated language.
IFB299 042 | FOUTWO-41 | Personal reminders | Story | Open | Could Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:51 | 2015-08-25 01:51 | 2015-08-25 01:51 | 0 | 1 | User story : ● As a user, I want to be able to develop my personal notes to save list important stuff so that I am able to implement my stuff progressively. Acceptance Criteria : ● Save or record down the stuff written by users. ● The list of stuff is recorded according to the prioritization.
IFB299 042 | FOUTWO-40 | Set up second password for file or folder | Story | Open | Could Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:50 | 2015-08-25 01:50 | 2015-08-25 01:50 | 0 | 1 | User story : ● As a user, I want to be able to add second password to my media file so that it ensures all my items are safe and secure. Acceptance Criteria : ● Add security password to specific files. ● Deny access to media files when password is wrong ● Pop-up the window to notify user whether password is wrong or correct
IFB299 042 | FOUTWO-39 | Account Setting | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:50 | 2015-08-25 01:50 | 2015-08-25 01:50 | 0 | 1 | User Story: ● As a user, I want to be able to add personal details such as name, birth date, and hobby, country of residence so that I am able to find friends with common interest. Acceptance Criteria : ● Allow user to complete list of their personal information. ● Allow to show their personal information to public or private.
IFB299 042 | FOUTWO-38 | Questions and Answers | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:49 | 2015-08-25 01:49 | 2015-08-25 01:49 | 0 | 1 | User story: ● As a system administrator, I want to be able to set up a webpage and update information regularly containing the most popular Q & A according to feedback so that I can let users use media vault more convenient. Acceptance criteria: ● Provide a webpage showing Q & A information Notes: ● Update information every 1 month ● Edit Q & A manually
IFB299 042 | FOUTWO-37 | The normalization of username and password | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:47 | 2015-08-25 01:48 | 2015-08-25 01:48 | 0 | 1 | User story: ● As a user I want the system to request the security level of user name and password so that my account is more secure. Acceptance criteria: ● Remind users to input their right account. ● Limit the length and form of the entry. Notes: ● The normative username and password are necessary when someone create his account. Alphanumeric combination is better than numbers combination, especially in security terms. ● User name should not include punctuation and between 8 to 20 characters. ● Password should not include punctuation and must have at least one capital. ● The length of password is between 8 to 20 characters.
IFB299 042 | FOUTWO-36 | Password Cache | Story | Open | Could Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:46 | 2015-08-25 01:46 | 2015-08-25 01:46 | 0 | 1 | User story: ● As a user, I want the system to remember my username and the password so that I can login directly. Acceptance criteria: ● Build a cache system to save the security details of users in local device.
IFB299 042 | FOUTWO-35 | Enable domain name access | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:45 | 2015-08-25 01:46 | 2015-08-25 01:45 | 0 | 1 | User story: ● As a user, I want to be able to enter domain name of the media vault so that I can find the webpage and enter user account and password quickly Acceptance criteria: ● System registers a free domain name ● The name of domain is easy-to-remember Notes: ● Almost all users do not want to use the IP address to find the media vault webpage, because a series of number is hard to remember. (e.g. www.team42mediavault.com)
IFB299 042 | FOUTWO-34 | External access (WAN) | Story | Open | Could Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:45 | 2015-08-25 01:45 | 2015-08-25 01:45 | 0 | 1 | User story: ● As a user, I want to access my media vault anywhere so that I can use the wide area network to enter my cloud drive rather than local area network. Acceptance criteria: ● Establish an outside access setting ● Use Raspberry Pi as the web server
IFB299 042 | FOUTWO-33 | Upload user head photo | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:44 | 2015-08-25 01:44 | 2015-08-25 01:44 | 0 | 1 | User story: ● As a user, I want to be able to upload my head portrait so that I can have a personalized user account. Acceptance criteria: ● Provide an area to upload user head portrait Notes: ● The size of head photo is no more than 500KB ● Only jpg format can be uploaded ● One head photo is allowed to be updated at the same time
IFB299 042 | FOUTWO-32 | View media vault in grid model | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:43 | 2015-08-25 01:43 | 2015-08-25 01:43 | 0 | 1 | User story: ● As a user, I want to be able to view my media vault in grid model, so that I can see basic information(thumbnail for pictures) of my media items. Acceptance criteria: ● Format thumbnail styles for pictures. ● All media types except pictures have their unique icon-design.
IFB299 042 | FOUTWO-31 | View media vault in list model | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:42 | 2015-08-25 01:43 | 2015-08-25 01:43 | 0 | 1 | User story: ● As a user, I want to be able to view my media vault in list model, so that I can see complete information of my media items. Acceptance criteria: ● Provide a vertical layout to show detailed information(date, size) Notes: ● Default layout is in list model ● All media types in list model have unified icon
IFB299 042 | FOUTWO-30 | Show detailed media information | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:42 | 2015-08-25 01:42 | 2015-08-25 01:42 | 0 | 1 | User story: ● As a user, I want to be able to see detailed information of my media items so that I can easily manage my files. Acceptance criteria: ● Detailed information includes: name/type/date uploaded/date modified/size/favourite ● Detailed information need to be used for sorting
IFB299 042 | FOUTWO-29 | Background music of interface | Story | Open | Could Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:41 | 2015-08-25 01:41 | 2015-08-25 01:41 | 0 | 1 | User story: ● As a user, I want to customize the background music for my so that I will not feel bored when managing my media files. Acceptance criteria: ● A media play activeX to play background music is used. ● Only music stored in the vault can be set as background music.
IFB299 042 | FOUTWO-28 | Backgroud color of interface | Story | Open | Could Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:41 | 2015-08-25 01:41 | 2015-08-25 01:41 | 0 | 1 | User story: ● As a user, I want to be able to change the backgroud color of interface as my favourite color. (optional) Acceptance criteria: ● Provide a drop-down box for users to edit background color.
IFB299 042 | FOUTWO-27 | Recently documents | Story | Open | Could Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:40 | 2015-08-25 01:40 | 2015-08-25 01:40 | 0 | 1 | User story: ● As a user, I want to be able to view the most recent document in the first place, so that I can find them quickly when I want to use it again. Acceptance criteria: ● Most 10 recently used document can be shown in a specific place (folder). ● Arrange the mostly used document according to date used in sequence.
IFB299 042 | FOUTWO-26 | Contact us and feedback | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:40 | 2015-08-25 01:40 | 2015-08-25 01:40 | 0 | 1 | User story: ● As a user, I want to be able to give feedbacks to system administrator, so that I can gain better user experience. Acceptance criteria: ● Users can send feedbacks by email (contact us). ● The categories of feedbacks can be chosen by users. e.g. suggestions, complaint and enquiries.
IFB299 042 | FOUTWO-25 | Delete media files and folders | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:39 | 2015-08-25 01:39 | 2015-08-25 01:39 | 0 | 1 | User story: ● As a user, I want to be able to delete my media files and folders completely so that I can delete what I do not need and release my storage. Acceptance criteria: ● Any deleted file or folder will be put into recycle bin ● Only files in recycle bin can be completely deleted
IFB299 042 | FOUTWO-24 | Drop media items and folders in recycle bin | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:38 | 2015-08-25 17:46 | 2015-08-25 17:46 | 0 | 1 | User story : ● As a user, I want to be able to delete my files temporarily or permanently in recycle bin so that I can retrieve my files and when I delete them by accident. Acceptance criteria : ● Permanent or temporary delete of media files ● Drop unused media files in trash temporarily ● Temporarily files can be retrieved ● Bin size is 1GB
IFB299 042 | FOUTWO-23 | Tooltip | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:38 | 2015-08-25 01:38 | 2015-08-25 01:38 | 0 | 1 | User story: ● As a user, I want to be able to give some tips so that I can easily use my media vault. Acceptance criteria: ● Build tooptip for buttons(function) to guide users on how to use it
IFB299 042 | FOUTWO-22 | Help request | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:38 | 2015-08-25 01:38 | 2015-08-25 01:38 | 0 | 1 | User story: ● As a user, I want to get instructions about the media vault so that I can check how to use the media vault when I face a problem. Acceptance criteria: ● Provide a webpage containing a list of instructions for a new user
IFB299 042 | FOUTWO-21 | Calculate storage capability | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:25 | 2015-08-25 01:37 | 2015-08-25 01:30 | 0 | 1 | User story: ● As a user, I want to be able to check the storage condition so that I can see how much space I have used and how much space I can use. Acceptance criteria: ● Design an area to show the storage capability information to users.
IFB299 042 | FOUTWO-20 | Redemption for storage expansion | Story | Open | Could Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:24 | 2015-08-25 01:31 | 2015-08-25 01:31 | 0 | 1 | User story : ● As a user, I want to be able to expand my storage space so that I can store more media files. Acceptance criteria : ● Expand storage manually (click button or show a pop-up window when user can expand storage space). Notes: ● Gain 1 point when upload 1 file ● If more points are gained, system will provide more storage space ● The points criteria are shown below: ● 100points, 1GB ● 190points, 2GB ● 270points, 3GB ● 340points, 4GB ● 400points, 5GB
IFB299 042 | FOUTWO-19 | Media playback in browser | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:23 | 2015-08-25 01:31 | 2015-08-25 01:31 | 0 | 1 | User story: ● As a user, I want to be able to view/consume my media within the application so that I don’t need to store it on my local device to view. Acceptance criteria: ● Calling a media play activeX to view media items(photo,music,video,PDF) online ● Photos can be displayed. ● EBooks can display a particular page and allow movement through the book. ● Audio and video files can be streamed to a particular device for playback.
IFB299 042 | FOUTWO-18 | Download media | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:18 | 2015-08-25 01:30 | 2015-08-25 01:30 | 0 | 1 | User story: ● As a user, I want to download media files so that I can save media items in my local device. Acceptance criteria: ● Any media files in user's media vault can be downloaded.
IFB299 042 | FOUTWO-17 | Upload media - Photos, Videos, Music, Ebook | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:17 | 2015-08-25 19:00 | 2015-08-25 01:31 | 0 | 1 | User story: ● As a user, I want to upload multiple file types so that I can store all of my media. Acceptance criteria: ● Photos, videos, music and Ebook can be uploaded ● Any file types outside of these cannot be uploaded(mp3/mp4/jpg/PDF)
IFB299 042 | FOUTWO-16 | Save shared media files from others | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:16 | 2015-08-25 01:31 | 2015-08-25 01:31 | 0 | 1 | User story: ● As a user, I want to be able to save shared media files from others after open the shared link so that I can add others’ files in my own media vault. Acceptance criteria: ● Provide a button (save in my vault) to save in user’s vault ● Provide a pop-up window for user to decide where to save (file path)
IFB299 042 | FOUTWO-15 | Share media files | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:16 | 2015-08-25 01:31 | 2015-08-25 01:31 | 0 | 1 | User story: ● As a user, I want to be able to share my media items so that I can share my files to other users. Acceptance criteria : ● Provide a link of the specific media items with an identification code which is used for authorization.
IFB299 042 | FOUTWO-14 | Title and description on uploads | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:15 | 2015-08-25 01:31 | 2015-08-25 01:31 | 0 | 1 | User story: ● As a user, I want to be able to input title and description to describe what I have uploaded so that I can fully understand the content. Acceptance criteria : ● Provide an area to write the title and description ● Description can be used for searching the certain media file
IFB299 042 | FOUTWO-13 | Search media | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:15 | 2015-08-25 01:32 | 2015-08-25 01:32 | 0 | 1 | User story: ● As a user, I want to be able to search my media so that I can easily find items I want. Acceptance criteria: ● Provide a custom search bar ● Use key words to search, including title and description
IFB299 042 | FOUTWO-12 | Sort media | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:13 | 2015-08-25 01:32 | 2015-08-25 01:32 | 0 | 1 | User stories: ● As a user, I want to be able to sort my media so that I can easily find items I want. Acceptance criteria ● Sort by type: Drop down box - media types(mp3/mp4/jpg) ● Sort by name: Alphabetical ● Sort by date uploaded: Recently to previously ● Sort by size:Min to max/ max to min ● Sort by date modified: Recently to previously ● Sort by favourite
IFB299 042 | FOUTWO-11 | Drag and drop media to vault | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:12 | 2015-08-25 01:32 | 2015-08-25 01:32 | 0 | 1 | User story: ● As a user, I want to be able to drag and drop my media into the vault or between different folders so that I can save time. Acceptance criteria ● Ability to drag only valid media types ● Dragged to another folders is allowed.
IFB299 042 | FOUTWO-10 | Rename item and folder | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:12 | 2015-08-25 01:32 | 2015-08-25 01:32 | 0 | 1 | User story: ● As a user, I want to be able to rename media file and folder so that I can fully understand the media files and folders. Acceptance criteria: ● System provides a function to rename the items and folders
IFB299 042 | FOUTWO-9 | Create folder | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:08 | 2015-08-25 17:59 | 2015-08-25 01:32 | 0 | 1 | User story: ● As a user, I want to be able to create folders so that I can easily manage my media items. Acceptance criteria: ● Folder name can be renamed ● Folders can be organized
IFB299 042 | FOUTWO-8 | Modify password | Story | Open | Must Have | Unresolved | Tee Ken Lau | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:08 | 2015-08-25 01:32 | 2015-08-25 11:36 | 0 | 1 | User story: ● As a user, I want to be able to modify my password so that I can keep my account secure. Acceptance criteria: ● Provide a pop-up webpage for user to modify password Notes: ● Should input old password in advance ● New password must be confirmed.
IFB299 042 | FOUTWO-7 | Find lost user name and password | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:07 | 2015-08-25 01:32 | 2015-08-25 01:32 | 0 | 1 | User story: ● As a user, I want to be able to find my user name and password via verified email so that I can find them if i forgot my user name and password. Acceptance criteria: ● Provide a text box for user to type verified email ● System will send the user name and password to verified email
IFB299 042 | FOUTWO-6 | Log out from media vault | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:05 | 2015-08-25 01:32 | 2015-08-25 01:32 | 0 | 1 | User story: ● As a user, I want to be able to log out from my media vault so that I can make sure my media vault secure when I leave. Acceptance criteria: ● Provide a button to log out ● Provide a pop-up window to notify that user has logged out successfully
IFB299 042 | FOUTWO-5 | Login with verified email address | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:05 | 2015-08-25 01:32 | 2015-08-25 01:32 | 0 | 1 | User story: ● As a user, I want to be able to login use my verified email address so that I can access my vault if I forgot my user name. Acceptance criteria: ● Provide a process to link user account and email ● Need to verify email address Notes: ● One user account can only be linked with one email address
IFB299 042 | FOUTWO-4 | Create user accounts for log in | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:04 | 2015-08-25 01:32 | 2015-08-25 01:32 | 0 | 1 | User story: ● As a User, I want to be able to login using the account I created or associated verified email address so that I can manage my own media items and my media is secure. Acceptance criteria: ● Username and password to login ● Need to verify email address ● Each user should be given a certain amount of space in the vault(5GB) ● Provide a process to check whether the account is unique
IFB299 042 | FOUTWO-3 | Mark as favourite | Story | Open | Should Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:01 | 2015-08-25 01:33 | 2015-08-25 01:33 | 0 | 1 | User story: ● As a user, I want to be able to mark chosen media items as favourite so that I can easily find my favourite media. Acceptance criteria: ● Favourite files can be shown in a specific folder. ● There is a favourite mark in detailed information.
IFB299 042 | FOUTWO-2 | Browse the media vault on mobile phone | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 01:00 | 2015-08-25 01:33 | 2015-08-25 01:33 | 0 | 1 | User story: ● As a user, I want to be able to access from mobile (mobile standard) so that I can browse my media in a small screen, which is easy to operate in a small screen. Acceptance criteria: ● Must have separate CSS documentation for mobile users (media query) ● The layout is different from that in desktop standard
IFB299 042 | FOUTWO-1 | Browse the media vault on laptop | Story | Open | Must Have | Unresolved | Unassigned | Zhengjie Yang | Zhengjie Yang | 2015-08-25 00:59 | 2015-08-25 18:55 | 2015-08-25 01:33 | 0 | 1 | User story: ● As a user, I want to be able to access from laptop(desktop standard) so that I can browse my media in a big screen to fully view my media files Acceptance criteria: ● Runs in browser, web based platform PHP/SQL
Generated at Tue Aug 25 19:02:38 EST 2015 by Zhengjie Yang using JIRA 6.2.7#6265-sha1:91604a8de81892a3e362e0afee505432f29579b0.